## Slide 1
Introduction
The Eastern region of Uganda had Viral Load coverage of 86.0%. Five districts of Bukedi sub-region had Viral load coverage 84 %.
This was sub-optimally low compared to 95% target of UNAIDS for HIV epidemic control.
The overall Turn around time for Viral load result was 25 days against the National target of 14 days.
The delay process of 11 days was between sample transportation from spoke facility to hubs at Busolwe and Pallisa Hospital.
This resulted into 50% Viral load samples delivered at hub within 2 days. This was attributed to delayed packaging of samples at spoke facility, online TAT tracker data not utilized.
USAID LPHS-E supported this study to reduce turn around time for viral load.
Methods
Results
Higher frequency visits by riders (thrice a week) to high volume facilities improved overall turn around time for viral load.
Conclusion
Lessons Learnt
Acknowledgements
Mapped 20 high volume facilities in Bukedi sub-region districts of Pallisa, Kibuku, Butaleja, Budaka and Butebo.
Changes to Improve Viral Load results Turn Around Time from Collection date to laboratory hub included;
  Hub Rider Thrice visit per week to facility,
  Hub driver visited hub on Second and Fifth day, rider reminder calls to facility to prepare samples,
  Health workers made Revisit calls to riders
  Facilitated hub rider to work on Weekends-Saturday,
  Lab Managers reviewed TAT weekly, Hub coordinator and LPHS-E Lab Officer reviewed riders online tracker weekly.
USAID -Local Partner Health Services-Eastern Region Activity (LPHS-E), Eastern region, Baylor College of Medicine-Uganda
Pallisa District Local Government, Pallisa General Hospital, Pallisa, Uganda.
Butaleja District Local Government, Busolwe General Hospital, Pallisa, Uganda.
Discussion
How to Reduce Viral Load Turn Around for Sample Transportation Between Spoke Health Facility and Laboratory Hub: A Case Study of Bukedi Region, Eastern Uganda
R. Mangeni11, S P. Okot1, P. Oballa1, D. Busharizi Migisha1, A. Katawera1, W. Akobye1, P. Tumbu1, M. Opio2, G. Mulekwa3, D. Wabusa4, JV Maliro5
Affiliation: 1USAID Local Partner Health Services – Eastern Activity (LPHS-E), 2 Kween District Local Government.,3Pallisa District Local Government, Pallisa General Hospital,4Butaleja District Local Government, 5Busolwe General Hospital, Pallisa, Uganda
The percentage of viral load samples delivered at Hub in 2days from 20 facilities increased from 50% to 100% by 16- May 2022.
Further within 3 months, overall 699/792 (88%) Viral Load samples were delivered at Hub in 2 days.
The overall turn around time from samples collection to results printing reduced from 25 days to 18 days close to the national target of 14 days.
Turn around time for results improved through cohesive coordination between the health workers and hub riders.
Chart: 
| 04 April 2022 | 11 April 2022 | 18 April 2022 | 25 April 2022 | 02 May 2022 | 09 May 2022 | 16 May 2022 | 23 May 2022 | 30 May 2022 | 06 June 2022 | April | May | June
# of VL samples delivered at Hub in 2days | 32 | 35 | 91 | 79 | 75 | 62 | 54 | 55 | 111 | 115
# of VL Samples Collected | 64 | 65 | 94 | 87 | 84 | 64 | 54 | 56 | 119 | 115
% VL samples delivered at Hub in 2 days | 0.5 | 0.53846 | 0.96809 | 0.90805 | 0.89286 | 0.96875 | 1 | 0.98214 | 0.93277 | 1
This poster was printed with the assistance of the American People through the United States Agency for Development (USAID).
Ministry of Health